## TEMPLATE FROM D-TOOLS
SOFTWARE ROLLOUT PLAN TEMPLATE | [7 empty] | FIND OUT WHICH D-TOOLS PRODUCT IS RIGHT FOR YOU
Software Title; Rollout Manager | [5 empty] | LAUNCH DATE: | 2022-06-01
OBJECTIVES |  |  | ACTIONS |  |  |  | CHECKPOINT | ADDITIONAL INFORMATION / NOTES
DATE | GOAL | PARTICIPANTS | STEP 1 | STEP 2 | STEP 3 | STEP 4
2022-05-11 | Introduce software to key leaders | Leadership team | Announce new software application during leadership team meeting | Send leadership team members login instructions | Have the leadership team explore the application and watch video tutorials | Have the leadership team customize their profiles within the application | Meet with the leadership team to receive feedback on the new software application and the training process
2022-05-18 | Develop a pilot program | Leadership team and pilot program testers | Ask each leader to identify a few people on their team to test the new software application | Provide login information to team members that are participating in the pilot program | Have leaders train these team members to use the software application | Ask these team members to customize their profiles within the application | Ask everyone who participated in the pilot program to complete a survey to share their feedback on the new software application and the training they received
2022-05-25 | Refine the onboarding process | Leadership team | Meet with the leadership team to review the feedback surveys from the pilot program | Identify areas for improvement and make necessary changes | Create accounts for everyone in the company | Set up profile fields and establish permissions | Have each leader notify the rest of the implementation team when they have created all the profiles for the employees they plan to train
2022-06-01 | Launch the software application | Leadership team and all employees | Introduce the new software application at the company-wide | Provide login information to every member of the team Screen reader support enabled. | Have leaders train team members to use the software application | Begin using the new software application to communicate with all team members | Ask each member of the team to complete a survey at the end of the week to share their feedback about the new software application and the training they received
Source for suggestions: Indeed